## Punch list
Odds Primer — Mobile Pre-Launch Punch List
Reconciled from two reviews · reviewed at 390×844 · 20 May 2026 · Claude = browser-verified, ChatGPT = text-only/lower confidence
ID | Priority | Page / Area | Issue | Recommended fix | Source | Confidence | Status
B-1 | Blocker | Site-wide (root cause) | oddsprimer.com serves TWO sites at once: the React editorial app AND the legacy static 'PredictionEdge' site (site/generate.py). They collide at /, /about, /matches, /outrights. This is the source of most blockers below. | Decide which system owns which routes. Either retire the static site, or scope it to non-conflicting paths and point the React app at the rest. Reconcile before anything else — most items below dissolve once this is resolved. | Claude B-3/B-4/B-6 + ChatGPT #1/#6 | High | Open
B-2 | Blocker | React app: /, /matches, /outrights, /m/*, /o/* | Verdict cards (.lv-card) overflow the right edge — no right padding, children render wider than the card, text clipped ('TRADE ON POLYMARKE', 'Mexico v South A'). Whole page scrolls sideways (240px content vs 199px viewport). | frontend/src/op/ card CSS: add overflow:hidden; width:100%; box-sizing:border-box to .lv-card and children; restore padding-right:16px. | Claude B-2 | High | Open
B-3 | Blocker | React app header (all routes) | Hamburger ☰ opens a 240px menu anchored right:0 to a tiny <details> element ~36px from the edge, so it extends ~57px off the LEFT of the screen. Menu items illegible. | frontend/src/op/ header CSS: position:fixed; right:0; top:0 with width:min(280px,100vw); max-width:100vw. Or make header relative+overflow:hidden and anchor the menu to it. | Claude B-1 / S-2 | High | Open
B-4 | Blocker | /about (no trailing slash) | Returns a bare 'HTTP Status: 404' white page. The home pill-nav 'About' links here, so every visitor tapping it hits the 404. | Add server/CDN redirect /about -> /about/ (or route both in the React app). | Claude B-3 | High | Open
B-5 | Blocker | 404 fallback (any bad URL) | Non-existent URLs serve the OLD static index ('PredictionEdge' title, wrong copy) with HTTP 200, not a real 404. | site/generate.py: ship a branded 404.html that links home; ensure the server returns a real 404 status. | Claude B-6 | High | Open
B-6 | Blocker | /ledger | Old 'PredictionEdge' <title> + meta description, a different header (no masthead/edition strip), and horizontal overflow (320px on a 199px viewport). | frontend/src/ledger/: update title/meta; reuse the shared masthead + pill-nav; fix overflow. If Ledger stays separate, add <meta robots=noindex>. | Claude B-5 / N-2 | High | Open
B-7 | Blocker | Email signup | Lives ONLY in the old static /index.html, ~7,250px down the page. The React app that serves oddsprimer.com/ has NO signup at all. Even the static form is broken: action=/index.html, method=GET, email input has no name attr -> submits nothing. No inputMode/autocomplete. | Add the signup to the React home page (and footer); wire to a real backend (Beehiiv/ConvertKit) with POST; input type=email name=email inputMode=email autocomplete=email required; add success + error states + operator/privacy line. | Claude B-7 + ChatGPT #3 | High | Open
B-8 | Blocker | /backtest | Full-page horizontal scroll (703px). Fixed-pixel grid (grid-template-columns:342px) + an unwrapped 679px <table>. Stat labels clipped, table right-half invisible. | site/generate.py CSS: grid -> repeat(2,1fr) + 1fr on mobile; wrap table in overflow-x:auto; container width:100%; padding:0 16px; box-sizing:border-box. | Claude B-8 | High | Open
B-9 | Blocker | Home / | Hero ('The 2026 World Cup, priced.') + intro + verdict KEY all sit before the first actual verdict. On a phone the Pick/Pass/Avoid — the product — is below the fold. (Conflicts with your locked rule: homepage must lead with the verdict.) | Move the headline verdict directly under the masthead/issue line; put the verdict key BELOW the first card. | ChatGPT #2 (aligns w/ locked priority) | High | Open
B-10 | Blocker | Legacy /events/:slug URLs | Old indexed event URLs (e.g. Colombia v Portugal, Panama v Croatia) return 404 — search traffic lands on dead pages. | VERIFY on device, then add redirects /events/:slug -> /m/... (or a branded fallback). | ChatGPT #4 | Verify | Open
S-1 | Should-fix | Static pages (/about/, /learn, /methodology, /responsible-use, /corrections, /method.html) | 350px 'On this page' sidebar (aside.content-rail) never collapses on mobile -> page is 370px wide, persistent horizontal scroll, every line clipped ('Prediction ma…'). | site/generate.py CSS: @media(max-width:640px){.content-rail{display:none}}; article max-width:100%; box-sizing:border-box. | Claude B-4 | High | Open
S-2 | Should-fix | Static pages | Different visual identity from the React app: purple/violet wordmark, heavier serif headings, different header/nav. Tapping About/Learn feels like a different website. | site/generate.py: adopt the shared CSS vars + masthead/edition-strip/pill-nav; wordmark color --color-masthead #0E2240, not violet. (Folds into B-1 once route ownership is decided.) | Claude S-1 + ChatGPT #6 | High | Open
S-3 | Should-fix | All pages — social sharing | No og:title / og:description / og:image / twitter:card anywhere. Shared links unfurl as blank cards in iMessage/WhatsApp/X — and sharing match picks is the main viral mechanic. Meta description is one generic site-wide line. | Add per-page OG/Twitter tags + a 1200x630 share image. Prioritize home + per-match pages. | Claude S-3 / N-1 / S-11 | High | Open
S-4 | Should-fix | Tap targets (verdict cards + nav) | Below 44px: 'Read the case →' 31px, 'See all…' ~32px, hamburger button 36px, pill-nav 38px, footer links 18px. | Extend hit areas to >=44px via min-height + inline-flex/align-items:center (no visual size change needed). Footer links: padding:8px 0. | Claude S-4/S-5/S-6/N-3 + ChatGPT #1 | High | Open
S-5 | Should-fix | Static pages — cookie banner | Cookie dialog is position:absolute and sits on top of the hero heading on first visit, scrolling with the page. | position:fixed; bottom:0; left:0; right:0; z-index:1000. | Claude S-7 | Medium | Open
S-6 | Should-fix | /method.html | PICK ¦ PASS ¦ AVOID tab strip overflows right; 'AVOID' clipped and untappable. | site/generate.py: flex-wrap:wrap + gap, or reduce min tab width so all three fit at 199px. | Claude S-8 | Medium | Open
S-7 | Should-fix | Static nav URLs | Menu links to /about/about.html, method.html, learn.html etc. — .html leaks into the URL bar; /about/about.html is confusing double-nesting; permanent if shared. | site/generate.py: emit clean paths (folder/index.html); point 'About' at /about/ not /about/about.html. | Claude S-9 / S-10 | Medium | Open
S-8 | Should-fix | Static edition strip | Shows 'UPDATED 13 MAY 2026' (7 days stale) and a hardcoded matchday. Undercuts a 'live markets desk'. React app says 'VOL.1' with no matchday — also inconsistent. | site/generate.py: derive date from build time / data layer; reconcile masthead/date/footer copy across both systems. | Claude S-12 / N-7 + ChatGPT #6 | Medium | Open
S-9 | Should-fix | Legal + signup — operator identity | Privacy says 'not a registered company' but omits the operating entity. Signup has no entity line. | Add 'Adi Dagan t/a Odds Primer' to Privacy, Terms, and signup consent micro-copy. | Claude B-7 + ChatGPT #5 | Medium | Open
S-10 | Should-fix | /learn structure | Appears to be ONE long primer with on-page anchors, not the expected three separate primers / tappable cards. | VERIFY; then either build 3 primer routes+cards (Prediction markets / Implied probability / Pick-Pass-Avoid) or reset the launch expectation. | ChatGPT #5 | Verify | Open
S-11 | Should-fix | /matches | 72 fixtures rendered sequentially, unfiltered — heavy and hard to scan on a phone. | Add sticky mobile filters (All / Picks / Pass / Avoid) + a 'Next 7 days' default. | ChatGPT #2 | Medium | Open
S-12 | Should-fix | Outright detail | 'Argentina +6.5pp but doesn't clear the +3pp Pick gate' reads as a contradiction without explanation. | Add one plain-English line: 'The point estimate is wide, but the confidence check isn't strong enough.' | ChatGPT #4 | Medium | Open
S-13 | Should-fix | Verdict key + About — voice | 'Pick the line is underpriced — back it' is too tipster-like; About's 'before acting elsewhere' is too action-oriented for an educational stance. | 'Pick — the line appears underpriced'; 'before visiting the source market'. | ChatGPT #6 / #7 | Medium | Open
S-14 | Should-fix | Match/home cards — CTA density | Polymarket + best-price + Kalshi + 'Read the case' run together — cramped at 390px. | Stack on mobile: full-width primary CTA, then secondary venue link, then 'Read the case'; all >=44px. | ChatGPT #1 | Medium | Open
N-1 | Nice-to-have | Pill-nav | Scrolls horizontally but no overflow hint — first-time users may not realize there are more items ('Winners' clipped). | Add a right-edge fade gradient (::after linear-gradient to bg). | Claude S-6 / N-4 | Medium | Open
N-2 | Nice-to-have | /backtest title + meta | Title encodes the build date ('The Desk · Backtest · 2026-05-08') — goes stale / breaks bookmarks. No meta description. | Permalink title; show date in body only; add a meta description; decide noindex. | Claude S-11 / N-5 | Medium | Open
N-3 | Nice-to-have | Footer | 7 legal links in one dense row on mobile. | Row 1: Responsible use / Affiliate / Corrections. Row 2: legal links. | ChatGPT #3 | Medium | Open
N-4 | Nice-to-have | Nav labels | Inconsistent: 'How it works' vs 'Method' vs 'Methodology'. | Pick one label site-wide (suggest 'Method'). | ChatGPT #2 | Medium | Open
N-5 | Nice-to-have | Home headline | 'The 2026 World Cup, priced.' is elegant but under-sells the verdict engine. | Optional: 'Every World Cup market, read by The Desk — Pick, Pass, or Avoid.' | ChatGPT #1 | Medium | Open

## Summary
How to read this
Root cause: oddsprimer.com is serving two sites at once — the React editorial app and the old static
'PredictionEdge' site (site/generate.py). Resolving B-1 (route ownership) collapses most other blockers.
Source reliability:
• Claude ran the live site at 390px and gives pixel-level evidence — treat as authoritative.
• ChatGPT could NOT load the site (worked from search-indexed text). Its 'couldn't find signup' and
'couldn't verify ledger/backtest' are non-findings — Claude verified all of those. Items marked
'Verify' (B-10, S-10) are ChatGPT-only and need a quick on-device check before acting.
Counts:
• Blockers: 10
• Should-fix: 14
• Nice-to-have: 5
Suggested order: (1) resolve the two-site conflict [B-1] — then re-test, many items vanish;
(2) the React-app CSS blockers [B-2, B-3]; (3) signup [B-7]; (4) verdict-led home [B-9]; (5) backtest [B-8].
Lane note: per spec-only mode, the website/design fixes here are yours to execute directly;
anything touching the engine/contract is Faktor's.